## Slide 1: Buy and Pay
DAP
Critical Business Impacts
10/31/13

## Slide 2: Critical Impacts Identified
Location/BU/ Service Line | Issue | Impact to the Business | Proposed Mitigation Strategy
DAP | No automatic migration of information from the current DAP SC Form to R12 Service Contracts. | Need to manually enter client information into Service Contracts for all DAP Clients (Approx. 900). We cannot start this migration until the “Go-Live” date of 10/7/13. | Starting on the “Go-Live” date, resources have been identified to start the manual process of migrating the data into Service Contracts. The goal is to have this task completed by 11/27/13.
DAP | No apparent access to, or availability of, required OBI Reports, such as: a) Direct-to-Order (DTO), b) DTO QA, c) CPM, High-Level View, d) Participant Search, and e) Scope Export for DAP Tool. | Need to manually create and maintain Excel spreadsheets for: a) annual list of DAP Participants for BU/Industry Lead Auditor audit project pre-assignment and assignment verification, b) monthly DAP Participant audit project and Lead Auditor assignment, c) verification of audit project creation and assignment, d) tracking of audit project progress and e) run scope reports in OBI ahead of time for any assessments taking place in the period between when we lose OBI and new reports are generated. | Schedule meeting with DAP SC Team to: a) review current condition and status of original DAP master client list, b) possibly incorporate the QA, CPM and other functionality into the master client list, and c) determine who and how the DAP master client list will be maintained. d) Long term would be to create new reports using OBEE or alternative to replicate the existing reports. This will take approx. 2 months.

## Slide 3: Additional Impacts (as of “Go-Live” 10/7)
Multiple ePro Profiles (R12 auto generates a New Work – No Test Profile). In DAP we use an “Audit Profile” for Audit Projects. We will need to push both profiles thru the process.
Co-existence of DAP Data. Use of My Home Tables to store DAP Data.
Not all DAP Clients have been migrated to R12. (Open ticket with IT)
Duplicate Customers with different Party Site Numbers – This has been effecting CAS New Work Projects.
DAP/MTL Scope Form – Auditors cannot add new signatories (we do have a work around). (Open Ticket with IT)